# 90-DAY EXECUTION PLAYBOOK

Phase 1: Foundation & Validation

March - June 2026 | Budget: $500K

# 1. Strategic Objectives

The 90-day Phase 1 sprint focuses on five critical objectives that de-risk the venture and position the company for successful seed funding close and Series A preparation. Each objective has measurable success criteria and specific ownership.

| # | Objective | Success Criteria | Owner |
| --- | --- | --- | --- |
| 1 | Team Assembly | VP Mfg + Arch Lead hired | Founder |
| 2 | Technical Validation | Gate 0 FPGA demo complete | Arch Lead |
| 3 | IP Protection | 3 provisionals + FTO opinion | Founder |
| 4 | Supply Chain Lock | LPDDR4 contract secured | VP Mfg |
| 5 | Community Foundation | GitHub + Discord + SDK | Founder |

# 2. Week 1-2: Critical Foundation

## 2.1 Day 1 Checklist

The following actions must be completed on Day 1 to establish momentum:

- Open VP Manufacturing job posting (LinkedIn, SemiWiki)

- Open Architecture Lead job posting (LinkedIn, IEEE)

- Engage patent counsel ($5K retainer)

- Order KV260 development board (~$300)

- Create GitHub organization (github.com/superinstance-ai)

- Create Discord server (discord.gg/superinstance)

- Reserve domain superinstance.ai (~$15)

- Email TeLLMe authors (arXiv:2510.15926)

- Email Tong Yang (PKU) - tongyang@pku.edu.cn

- Apply to Silicon Catalyst incubator

## 2.2 VP Manufacturing Hiring Sprint

The VP Manufacturing hire is CRITICAL and NON-NEGOTIABLE. The candidate must have 5+ successful tape-outs with AI/accelerator background. Compensation: $180-220K base + 2-4% equity + $25-50K signing bonus if needed. Recruiting channels: LinkedIn Recruiter, SemiWiki, Silicon Catalyst network, IEEE Solid-State Circuits Society, direct approach to Groq/Etched/Tenstorrent alums.

# 3. Week 3-4: Patent Filing & Supply Chain

## 3.1 Patent Filing Timeline

| Day | Activity | Deliverable |
| --- | --- | --- |
| Day 8-10 | Finalize P1 claims with counsel | Claim document |
| Day 11-14 | Prepare P1 drawings | Figure set |
| Day 15 | File P1 provisional | USPTO confirmation |
| Day 20 | File P2 provisional (RAU) | USPTO confirmation |
| Day 28 | File P3 provisional (Hybrid) | USPTO confirmation |

## 3.2 LPDDR4 Supply Contract Engagement

Contact strategy for LPDDR4 allocation (CRITICAL due to pricing crisis):

- Primary Target: Micron (US-based, CHIPS Act preference)

- Secondary Target: Samsung (Korean, established relationship)

- Contract Requirements: 50K units committed, $8-10 per 512MB, 24-month NCNR

- Allocation Cost: ~$500K (refundable against orders)

# 4. Week 5-8: FPGA Development

## 4.1 Gate 0 Milestones

The Gate 0 FPGA demonstration is the critical technical validation milestone:

| Week | Milestone | Deliverable |
| --- | --- | --- |
| Week 5 | Environment setup | KV260 booted, PYNQ installed |
| Week 5 | Model preparation | BitNet b1.58-2B-4T validated |
| Week 6 | bitnet.cpp integration | CPU inference working |
| Week 6 | FPGA synthesis start | RTL targeting KV260 |
| Week 7 | First synthesis | Design compiles, timing met |
| Week 7 | Bring-up begins | Hardware running inference |
| Week 8 | Performance validation | 25+ tok/s, <5W demonstrated |

# 5. Week 9-12: SDK & Community Launch

## 5.1 SDK Alpha Release

The SDK Alpha release targets PyPI publication with core functionality:

- Package Name: superinstance

- Version: 0.1.0a1 (alpha)

- License: Apache 2.0

- Python: 3.8+

- Installation: pip install superinstance --pre

## 5.2 Community Launch Targets

Launch metrics targets for Month 1:

- GitHub Stars: 500+ (Week 1)

- Discord Members: 300+ (Week 1)

- SDK Downloads: 1,000+ (Month 1)

# 6. Budget Allocation

| Category | Amount | Notes |
| --- | --- | --- |
| Team (3 months) | $145K | VP Mfg, Arch Lead, ML Eng |
| IP (Patents + FTO) | $40K | 3 provisionals + FTO opinion |
| Hardware/Equipment | $12K | KV260 boards, test equipment |
| Supply Chain Deposit | $100K | LPDDR4 allocation (refundable) |
| EDA Tools (6 months) | $50K | Cadence/Synopsys rental |
| Other (Legal, Cloud, Travel) | $53K | Corporate setup, compute, visits |
| TOTAL PHASE 1 BUDGET | $500K | - |

# 7. Phase 1 Exit Criteria

The following criteria must be met to successfully complete Phase 1 and advance to Phase 2:

- VP Manufacturing hired (Day 60 max)

- Architecture Lead hired

- 3 provisional patents filed

- FTO opinion received from counsel

- Gate 0 FPGA demo complete (25+ tok/s, <5W)

- SDK Alpha published to PyPI

- LPDDR4 allocation contract secured

- GlobalFoundries 22FDX engagement initiated

- 500+ GitHub stars

- 300+ Discord members

- Seed term sheet received